## Sheet1
No | Date (initial date) | Category | Motherboard | SW Spec |  | Feedback | Ready in EVT Status | Ready in DVT Status
1 | 2020-02-12 | BIOS | both | UEFI |  | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-22
2 | 2020-02-12 | BIOS | both | secure Boot according to the currently required security standards (Intel, Microsoft, etc.) | Note: For all safety-relevant BIOS properties, the risk must be represented by the vendor using a risk and thread analysis. | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-30
3 | 2020-02-12 | BIOS | both | secure BIOS-Update according to the currently required security standards (Intel, Microsoft, etc.) | using following method: "signed capsuled update". Inclusive Recovery BIOS Update selectable via Jumper (at the ATX Header); Note: For all safety-relevant BIOS properties, the risk must be represented by the vendor using a risk and thread analysis. | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-30
4 | 2020-02-12 | BIOS | both | Password protection in two levels | 1. level "USER" 2.level "Administrator" | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-22
5 | 2020-02-12 | BIOS | both | Plug and play |  | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-22
6 | 2020-02-12 | BIOS | both | ACPI |  | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-22
7 | 2020-02-12 | BIOS | both | PXE support |  | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-22
8 | 2020-02-12 | BIOS | both | Wake on LAN | WOL can be deactivated | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-30
9 | 2020-02-12 | BIOS | both | Boot on LAN | PXE can be selectively disabled for each LAN port. | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-30
10 | 2020-02-12 | BIOS | both | Boot on USB | boot from USB device should be forceble via BIOS switch | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-22
11 | 2020-02-12 | BIOS | both | Boot on M.2 NVMe |  | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-22
12 | 2020-02-12 | BIOS | both | Boot on SATA (all SATA modes) |  | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-22
13 | 2020-02-12 | BIOS | both | DMI area accessible for user | DMI area should be accessible for user - programm to write/read DMI area has to be provided Note: at least DMI data to be read and written by Siemens: Typ0 Offset 4;5;6;7 Typ3 Offset 4;5;6;7;8 Typ11 1. String; 2. String; 3. String Typ15 1. String; 2. String; 3. String | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-30
14 | 2020-02-12 | BIOS | both | Writing of SLIC table | Possibility (incl. tool) to embedded the following SLIC files into the DMI structure: PubKey.bin; Marker.bin | 13.02.2020 (Aaeon) SLIC is for Windows 7 only, if CML-S W480/H410 MBs need support Windows 7? If yes, please provide the public key. 13.02.2020 (Siemens) Win 7 is no longer supported with CML, we need the SLIC tables because of the pre-activation of the planned server operating systems. But: The SLIC tables may only be active if we deliver server operating systems. If for example no OS or Win10 is delivered (are possible delivery options) the SLIC tables must not be active. Current solution at Fujitsu is that we got a tool that allowed us to write the SLIC tables on demand. On the other hand, Microsoft has forbidden us to give away the public key. 18.02.2020 (Aaeon) If Siemens can provide us the public key, we can provide SLIC table. 25.02.2020 (Siemens) Okay, Siemens will hand over the "public key" to Aeon. But the open question (and therefore the method) of "selectively disabling the SLIC tables when no OS is delivered" is not clear to us. The method must be designed in a way that no customer is able to activate the SLIC tables, it must only be possible to do this from Siemens in production or in case of repair. 25.02.2020 (Aaeon) Aaeon can provide "selectively disabling the SLIC tables when no OS is delivered" function for customer requirement. (26.03.2020) Siemens I have received the instruction from my security officer that the SLIC part "Marker.bin" may not be given away. For this reason I have to renew the request to program the "Marker.bin" later in our production process. Please schedule a corresponding procedure. (06.04.2020) Aaeon Aaeon can provide SLIC table within one week once Siemens release the "Marker.bin". | 2020/5/8
15 | 2020-02-12 | BIOS | both | OEM BIOS default value parameterization | tool for writing/reading BIOS default values has to be provided | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-30
16 | 2020-02-12 | BIOS | both | Possibility of customer-specific logo | Siemens logo, Siemens look & feel | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-05-08
17 | 2020-02-12 | BIOS | both | USB Power switchable in BIOS |  | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-05-08
18 | 2020-02-12 | BIOS | both | Single / dedicated USB port can be switched on / off via BIOS Settings |  | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-05-08
19 | 2020-02-12 | Monitoring functions | both | Management controller | 3 Fan Characteristic necessary: Silent Performance Auto Disabled A configuration tool must be provided to configure the system temperature regulation (also for the manufacturing process). This means that the dependency between temperature sensor and fan must be parameterizable in the tool. (and that for the 3 above characteristics independently) The fan characteristic must also be parameterizable, for example: Minimum speed; slope of the control curve; alarm threshold | (26.03.2020) Siemens At the beginning of 05/20 we want to start directly with the type test (climate / EMC), for this purpose a basic functionality of the fan control and fan influence is absolutely necessary. Please check if an earlier date for this function (API and ready BIOS) can be enabled. The support for Linux etc. could be postponed until mid 06/20 at the latest. (06.04.2020) Aaeon Siemens could do the test at the beginning of 05/2020. | 2020/5/22-ready in BIOS 2020/05/22-API Framework only 2020/05/07-API and BIOS ready for test 2020/05/22-Linux SDK ready on Ubuntu, Debian(this item contains all API functions and uni-test command line utility) 2020/05/29-Linux SDK ready on Fedora, OpenSUSE, Red Hat Enterprise, SUSE Enterprise | 2020/07/16-API/SW release
20 | 2020-02-12 | Monitoring functions | both | Temperature | only monitor via the API. several temperature sensors must be mounted on the motherboard (an overview picture where which sensor is installed is required). Minimum requirements CPU-VRM; Memory; PCIe Slots ( at the PEG Slot); at the SATA Ports (CPU and PCH via software). All sensors must be able to be integrated in the autonomous temperature regulation. | (26.03.2020) Siemens At the beginning of 05/20 we want to start directly with the type test (climate / EMC), for this purpose a basic functionality of the fan control and fan influence is absolutely necessary. Please check if an earlier date for this function (API and ready BIOS) can be enabled. The support for Linux etc. could be postponed until mid 06/20 at the latest. (06.04.2020) Aaeon Siemens could do the test at the beginning of 05/2020. | 2020/5/22-ready in BIOS 2020/05/22-API Framework only 2020/05/07-API and BIOS ready for test 2020/05/22-Linux SDK ready on Ubuntu, Debian(this item contains all API functions and uni-test command line utility) 2020/05/29-Linux SDK ready on Fedora, OpenSUSE, Red Hat Enterprise, SUSE Enterprise | 2020/07/16-API/SW release
21 | 2020-02-12 | Monitoring functions | both | Watchdog | should be monitored, can be configured to reset the system (via BIOS and via API) | (26.03.2020) Siemens The watchdog may be implemented at a later time, e.g. could be postponed until mid 06/20 at the latest. | 2020/5/22-ready in BIOS 2020/05/22-Linux SDK ready on Ubuntu, Debian(this item contains all API functions and uni-test command line utility) 2020/05/29-Linux SDK ready on Fedora, OpenSUSE, Red Hat Enterprise, SUSE Enterprise | 2020/07/16-API/SW release
22 | 2020-02-12 | Monitoring functions | both | Fans (all incl. power supply) | only monitor | (26.03.2020) Siemens At the beginning of 05/20 we want to start directly with the type test (climate / EMC), for this purpose a basic functionality of the fan control and fan influence is absolutely necessary. Please check if an earlier date for this function (API and ready BIOS) can be enabled. The support for Linux etc. could be postponed until mid 06/20 at the latest. (06.04.2020) Aaeon Siemens could do the test at the beginning of 05/2020. | 2020/5/22-ready in BIOS 2020/05/07-API and BIOS ready for test 2020/05/22-Linux SDK ready on Ubuntu, Debian(this item contains all API functions and uni-test command line utility) 2020/05/29-Linux SDK ready on Fedora, OpenSUSE, Red Hat Enterprise, SUSE Enterprise
23 | 2020-02-12 | Monitoring functions | both | CMOS battery monitoring | monitoring of the status and waning during the BIOS-boot if the thresholds are below the limits | (26.03.2020) Siemens The "CMOS battery monitoring" may be implemented at a later time, e.g. could be postponed until mid 06/20 at the latest. | 2020/5/22-ready in BIOS
24 | 2020-02-12 | Monitoring functions | both | SMART indicator for all SATA ports | only monitor; SMART data should be monitored and displayed through RAID BIOS and RAID driver (using CSMI interface) | (26.03.2020) Siemens The "SMART indicator" may be implemented at a later time, e.g. could be postponed until mid 06/20 at the latest. | 2020/5/22-ready in BIOS
25 | 2020-02-12 | Monitoring functions | SMS-W480 | Remote access | iAMT | (26.03.2020) Siemens For EVT the schedule is ok. | 2020/05/22-API Framework only | 2020/07/16-API/SW release
26 | 2020-02-12 | Monitoring software | both | Temperature | provide an API to give user programms (Siemens develops their own tool) access to monitor values. A separate tool for the monitor functionality is not necessary. | (26.03.2020) Siemens At the beginning of 05/20 we want to start directly with the type test (climate / EMC), for this purpose a basic functionality of the fan control and fan influence is absolutely necessary. Please check if an earlier date for this function (API and ready BIOS) can be enabled. The support for Linux etc. could be postponed until mid 06/20 at the latest. (06.04.2020) Aaeon Siemens could do the test at the beginning of 05/2020. | 2020/05/22-API Framework only 2020/05/07-API and BIOS ready for test 2020/05/22-Linux SDK ready on Ubuntu, Debian(this item contains all API functions and uni-test command line utility) 2020/05/29-Linux SDK ready on Fedora, OpenSUSE, Red Hat Enterprise, SUSE Enterprise | 2020/07/16-API/SW release
27 | 2020-02-12 | Monitoring software | both | Watchdog |  | (26.03.2020) Siemens The watchdog may be implemented at a later time, e.g. could be postponed until mid 06/20 at the latest. | 2020/05/22-API Framework only 2020/05/22-Linux SDK ready on Ubuntu, Debian(this item contains all API functions and uni-test command line utility) 2020/05/29-Linux SDK ready on Fedora, OpenSUSE, Red Hat Enterprise, SUSE Enterprise | 2020/07/16-API/SW release
28 | 2020-02-12 | Monitoring software | both | Fans |  | (26.03.2020) Siemens At the beginning of 05/20 we want to start directly with the type test (climate / EMC), for this purpose a basic functionality of the fan control and fan influence is absolutely necessary. Please check if an earlier date for this function (API and ready BIOS) can be enabled. The support for Linux etc. could be postponed until mid 06/20 at the latest. (06.04.2020) Aaeon Siemens could do the test at the beginning of 05/2020. | 2020/05/22-API Framework only 2020/05/07-API and BIOS ready for test 2020/05/22-Linux SDK ready on Ubuntu, Debian(this item contains all API functions and uni-test command line utility) 2020/05/29-Linux SDK ready on Fedora, OpenSUSE, Red Hat Enterprise, SUSE Enterprise | 2020/07/16-API/SW release
29 | 2020-02-12 | Monitoring software | both | Local monitoring software |  | (26.03.2020) Siemens At the beginning of 05/20 we want to start directly with the type test (climate / EMC), for this purpose a basic functionality of the fan control and fan influence is absolutely necessary. Please check if an earlier date for this function (API and ready BIOS) can be enabled. The support for Linux etc. could be postponed until mid 06/20 at the latest. (06.04.2020) Aaeon Siemens could do the test at the beginning of 05/2020. | 2020/05/22-API Framework only 2020/05/07-API and BIOS ready for test | 2020/07/16-API/SW release 2020/07/16-Linux Monitoring SW release(this item is for the SW SDK final release. It contains the bug fixes and the technical documents)
30 | 2020-02-12 | Monitoring software | both | DiagMonitor software support. (DiagMonitor = Siemens maintenance software package) We need support for all required OS (see below) and additional an LINUX interface to get the data within the manufacturing process. | A software interface (API) is necessary to control / monitor all Motherboard functions: eg.: Fan-Speed --> influence and monitoring Motherboard Temperatures (CPU, PCH, Memory; PEG) --> monitoring Watchdog --> influence Battery Status --> Monitoring Note: The structure of the API interface is contained in the RFQ. | 13.02.2020 (Aaeon) We didn't receive the structure of API, please provide it. 13.02.2020 (Siemens) The enclosed header file shows the API requirements of our software development. (26.03.2020) Siemens Because the entire monitoring concept is based on this API and an adaptation of our software is also required, the API is needed much earlier --> early 05/20. | 2020/6/5 2020/05/12
31 | 2020-02-12 | Operating systems | both | Windows 10 (64 bit) LTSC >= 2019 |  | (26.03.2020) Siemens For EVT the schedule is ok. | 2020/4/22-Driver release
32 | 2020-02-12 | Operating systems | SMS-W480 | Windows Server 2016 |  | 13.02.2020 (Aaeon) If Siemens will provide the Licence? 13.02.2020 (Siemens) The operating system licenses are billed directly to Microsoft. This requirement here refers to ensuring that Aaeon generally supports motherboards for this operating system. This means that Aaeon provides Siemens with qualified driver packages and offers support in case of problems. (26.03.2020) Siemens We need a driver set already in the EVT phase | 2020/05/25- first Driver release | 2020/7/3-Driver release
33 | 2020-02-12 | Operating systems | SMS-W480 | Windows Server 2019 |  | 13.02.2020 (Aaeon) If Siemens will provide the Licence? 13.02.2020 (Siemens) The operating system licenses are billed directly to Microsoft. This requirement here refers to ensuring that Aaeon generally supports motherboards for this operating system. This means that Aaeon provides Siemens with qualified driver packages and offers support in case of problems. (26.03.2020) Siemens We need a driver set already in the EVT phase | 2020/05/28- first Driver release | 2020/7/11-Driver release
34 | 2020-02-12 | Operating systems | both | Linux support | yes (64 Bit) | (26.03.2020) Siemens For EVT the schedule is ok. | 2020/4/30-Ubuntu, Debian basic installation test report 2020/5/7-Fedora, OpenSUSE, Red Hat Enterprise Linux, SUSE Linux Enterprise basic installation test report 2020/5/29-Linux OS support issue fix
35 | 2020-02-12 | Ease of service | both | Serial number | should be readable thru BIOS / user application | (26.03.2020) Siemens For EVT the schedule is ok. | 2020/5/8-ready in BIOS 2020/05/22-API Framework only | 2020/07/16-API/SW release
36 | 2020-02-12 | Ease of service | both | Product version (GS state) | should be readable thru BIOS / user application | 13.02.2020 (Aaeon) What does GS state mean? 13.02.2020 (Siemens) Siemens requires a unique (frozen) hardware release status of the motherboard, which uniquely defines an releasing hardware status. Fujitsu has used the GS-status for this purpose, Aaeon is free to call this hardware release status differently. (26.03.2020) Siemens For EVT the schedule is ok. | 2020/5/22-ready in BIOS 2020/05/22-API Framework only | 2020/07/16-API/SW release
37 | 2020-02-12 | Ease of service | both | BIOS update (Windows tool) | should be possible via software tool without installation required. Software tool must be provided | (26.03.2020) Siemens If Aaeon provides another possibility for a BIOS update until then, this date is ok. --> yes is with "UEFI Shell update" ok … line 41 | 2020-05-22
38 | 2020-02-12 | Ease of service | both | BIOS update (DOS tool) | should be possible via software tool without installation required. Software tool must be provided | 18.02.2020 (Aaeon) Since Siemens request the secure boot, Legacy BIOS update tool is not applicable. 25.02.2020 (Siemens) The requirement for a BIOS update under DOS is obsolete because of secure boot. Which possibility can Aaeon offer to perform a BIOS update (e.g. via USB-stick) without loaded OS? 25.02.2020 (Aaeon) Aaeon can update BIOS in EFI shell environment via USB-stick, which doesn’t need OS loaded. | N/A
39 | 2020-02-12 | Ease of service | both | BIOS update (UEFI Shell tool) | should be possible via software tool without installation required. Software tool must be provided | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-04-22
40 | 2020-02-12 | Ease of service | both | BIOS update Linux (for BIOS-update during manufactoring) | should be possible via software tool without installation required. Software tool must be provided Note: The DiagMonitor software has an function called “BIOS update”. This function make an procedure call to an particularly BIOS update tool provided from the motherboards vender. Therefore we need an remotely controllable BIOS update tool working under all required operation systems. | (26.03.2020) Siemens For EVT the schedule is ok. | 2020-06-05
41 | 2020-02-12 | Ease of service | both | Monitoring firmware update tool | should be possible via software tool without installation required. Software tool must be provided | (26.03.2020) Siemens At the beginning of 05/20 we want to start directly with the type test (climate / EMC), for this purpose a basic functionality of the fan control and fan influence is absolutely necessary. Please check if an earlier date for this function (API and ready BIOS) can be enabled. (06.04.2020) Aaeon Siemens could do the test at the beginning of 05/2020. | 2020/05/22-API Framework only 2020/05/07-API and BIOS ready for test | 2020/07/16-API/SW release
42 | 2020-02-12 | LED behavior | both | 15.01.2020 (Siemens) Thomas has sent the schematic of the LED-display-board to Vivian. All relevant data should be visible in this schematic. (Aaeon) Vivian has asked questions about it. Feedback will be provided. --> Thomas 20.01.2020 (Siemens): see the answers in the following Excel table: 20.01.2020 (Siemens) Aaeon needs detailed information about the single functions like blinking speed etc. --> thomas 30.01.2020 (Siemens) the only requirement is that in standby (S3) the green power LED flashes at intervals of 1s. The error messages you suggest (flashing states of the LED) are acceptable. (mail from Vivian on 20.01.2020) the blinking speed of the HDD Alram LED is reported to the GPIOs via API / software and therefore does not need to be defined. 30.01.2020 (Siemens) Note the Ecxel table (see above) has been extended regarding the LED requirements. 05.02.2020 (Aaeon) Aaeon still has special questions about the 24pin front interface (Mail: from Vivian "RE: LED behavior" from 04.02.2020) Thomas will answer the mail shortly. |  | (26.03.2020) Siemens At the beginning of 05/20 we want to start directly with the type test (climate / EMC), for this purpose a basic functionality of the fan control and fan influence is absolutely necessary. Please check if an earlier date for this function (API and ready BIOS) can be enabled. (06.04.2020) Aaeon Siemens could do the test at the beginning of 05/2020. | 2020/05/22-API Framework only 2020/05/07-API and BIOS ready for test | 2020/07/16-API/SW release
43 | 2020-02-12 | Fan control | both | 15.01.2020 (Aaeon) Siemens spec: 3 Fan Characteristic(Silent/Performance/Auto/Disabled) [Question] What’s the exactly definition of the 3 Fan characteristic? (ex. Silent definition is Fan PWM < a value). Where do we present these characteristic, through BIOS setup options or Windows application? | 15.01.2020 (Siemens) There is no closed specification for this. Thomas will create a description of what Siemens expect. 30.01.2020 (Siemens) see table, in which is describe how current with the current Fujitsu board the fan characteristics are parameterized: Siemens expects that Aaeon will provide comparable setting options. | (26.03.2020) Siemens At the beginning of 05/20 we want to start directly with the type test (climate / EMC), for this purpose a basic functionality of the fan control and fan influence is absolutely necessary. Please check if an earlier date for this function (API and ready BIOS) can be enabled. (06.04.2020) Aaeon Siemens could do the test at the beginning of 05/2020. | 2020/5/22-ready in BIOS 2020/05/07-API and BIOS ready for test